AI Workforce Implementation Pilot

Proposal for a Grant-Funded AI Workforce Implementation & Employment Specialist

Developed by Ryan Uher | Proposed Pilot Concept

# Executive Summary

This proposal outlines a 12–18 month AI workforce implementation pilot at the American Job Center Lincoln. The pilot would create a dedicated AI Workforce Implementation & Employment Specialist position responsible for translating emerging AI tools into practical, responsible workforce services for job seekers, staff and employers.

The position would lead implementation of AI Employment Navigator, provide AI literacy and job-search instruction, train staff on approved AI workflows, develop safeguards and procedures, evaluate tools, measure results and pursue sustainable funding. The initial goal is not to purchase a large new software system. The goal is to prove a service model using existing infrastructure and approved AI tools, then determine what level of technology investment is justified.

# Why Now

The U.S. Department of Labor issued an Artificial Intelligence Literacy Framework in February 2026 specifically encouraging expanded AI literacy across the public workforce system, including American Job Centers.

AJC Lincoln already provides walk-in job-search support, Resource Room access and digital-literacy referrals without an appointment or eligibility requirement.

AI is changing how employers recruit, how workers search and apply for jobs, and the skills workers need to stay competitive.

The Job Center needs a practical implementation role that can translate AI policy and technology into usable services, training, safeguards and measurable outcomes.

# Proposed Position

AI Workforce Implementation & Employment Specialist

A workforce-development implementation role—not a software-engineering position. The specialist would focus on adoption, training, workflow design, responsible use, staff support, participant services, project management and outcome measurement.

Lead the AI Employment Navigator pilot and universal-access Job Watch model.

Provide AI literacy and responsible-AI instruction to job seekers.

Train Career Planners and other staff on approved AI-assisted workflows.

Develop standardized prompts, guides, SOPs and participant materials.

Evaluate AI tools for practical workforce-service use.

Establish privacy, human-review, accuracy and responsible-use safeguards with leadership.

Track lead quality, applications, interviews, placements, staff time and participant feedback.

Develop workshops such as Build Your AI Job Search Assistant.

Support employer/community AI-literacy activities as approved.

Identify grant and sustainability funding for expansion.

# Pilot Structure

| Element | Proposed Approach |
| --- | --- |
| Duration | 12–18 months |
| Position | 1.0 FTE AI Workforce Implementation & Employment Specialist |
| Initial service model | Existing AJC computers, Resource Room, staff, NEworks, public job sources and approved LLMs |
| Participants | Universal-access job seekers plus selected program participants |
| Staff | Pilot group of Career Planners and front-door/resource-room staff |
| Evaluation | Usage, job lead quality, applications, interviews, placements, time savings, AI errors and feedback |
| Expansion decision | Scale, modify or stop based on evidence |

# Funding Strategy

The strongest approach is a braided strategy. The City/AJC would determine allowability with fiscal, program and legal/compliance staff before charging costs to any funding source.

Existing WIOA or workforce funds for allowable career-service, AI-literacy, staff-development or pilot activities.

Wagner-Peyser/Employment Service or One-Stop/Resource Room alignment where allowable and approved.

State workforce innovation or Governor's Reserve opportunities.

City or local workforce-development resources for costs that do not fit a federal funding stream.

Competitive federal or state AI-literacy, workforce-technology, reemployment, digital-literacy or innovation grants.

Foundation, higher-education, employer or community partnerships for curriculum, evaluation or technology access.

# Position-Creation Logic

The grant or pilot would fund a defined workforce innovation project. The specialist position would be a necessary project cost because implementation requires consistent ownership of training, tool evaluation, documentation, safeguards, measurement, staff support and grant reporting. This is more defensible than asking a funder to create a permanent position without a project.

# Measures of Success

Number of job seekers receiving AI-assisted employment support

Number of staff trained and workflows adopted

Qualified job leads generated and acted upon

Application-to-interview and interview-to-offer conversion

Employment placements

Participant and staff satisfaction

Staff/client search time saved

AI error/poor-match rate and corrective actions

Program referrals created through identified training or barrier needs

Sustainability funding identified

# Leadership Ask

Authorize development of a grant-ready 12–18 month AI workforce implementation pilot, including a proposed AI Workforce Implementation & Employment Specialist position, and allow the project lead to work with leadership, fiscal/compliance staff and eligible funding partners to identify the most appropriate funding path.

# Important Boundary

This concept does not assume that any particular grant or WIOA cost is automatically allowable. Funding decisions should be made by the appropriate City/AJC fiscal, program, legal and grant-management staff. The pilot should also use organization-approved AI platforms and maintain human review for consequential decisions.